HOPEBED

Founder / CEO — 3-Day Execution Plan

30 August 2026 → 1 September 2026

CEO objective: move Hopebed from planning to evidence — a stable MVP, real owner conversations, and 1–2 pilot properties.

1. CEO PRIORITIES

| P0 | Prove the MVP works | Stable website + core user/owner flow. |
| --- | --- | --- |

| P0 | Talk to the market | 5 real PG/hostel owners interviewed. |
| --- | --- | --- |

| P0 | Secure early supply | Aim for 1–2 pilot properties. |
| --- | --- | --- |

| P1 | Clean business foundation | Documents, compliance checks, agreements and policies organized. |
| --- | --- | --- |

| P1 | Protect focus | No ads, no unnecessary redesign, no advanced features yet. |
| --- | --- | --- |

2. THREE-DAY EXECUTION PLAN

| Day | Primary Goal | CEO Checklist | End-of-Day Output |
| --- | --- | --- | --- |
| DAY 1 — 30 AUG | MVP + Website QA | ☐ Desktop QA ☐ Mobile QA ☐ Test all navigation/CTAs ☐ Test Contact / WhatsApp ☐ Check images/CSS/JS ☐ Run PageSpeed Insights ☐ Check broken links ☐ Fix only critical issues | Website is stable enough for real user/owner testing. |
| DAY 2 — 31 AUG | Owner validation | ☐ Contact 5 owners ☐ Explain Hopebed in 30 sec ☐ Ask biggest booking problem ☐ Ask whether they would list ☐ Capture objections ☐ Record exact answers | 5 conversations completed; strongest pain point and 1–2 pilot candidates identified. |
| DAY 3 — 1 SEP | MVP flow + business readiness | ☐ Build/test user flow ☐ Build/test owner flow ☐ Test one real-property journey ☐ Check legal/business documents ☐ Check DPIIT eligibility ☐ Confirm next 7-day build priorities | Working end-to-end MVP path + clear business/compliance action list. |

3. BUSINESS & LEGAL FOUNDATION

Complete these checks in parallel with product work. Do not duplicate registrations already completed.

☐ Confirm Hopebed legal structure (company / LLP / partnership / other current form).

☐ Keep Udyam / MSME certificate and registration documents in one founder folder.

☐ Confirm PAN / TAN status as applicable.

☐ Confirm business bank-account status.

☐ Check GST requirement against the actual entity, turnover and business model; confirm with a CA before filing.

☐ Check eligibility for DPIIT Startup Recognition and prepare documents if eligible.

☐ Prepare a simple Property Partner / Pilot Agreement.

☐ Prepare Privacy Policy and Terms of Use for the website.

☐ Prepare a Property Verification Policy: Submitted → Under Review → Verified / Changes Required.

☐ Prepare owner consent for listing photos and property information.

☐ Keep official business email, website, contact details and founder records organized.

Founder folder recommendation:

01_Registration  |  02_Tax  |  03_Bank  |  04_Legal  |  05_MVP  |  06_Owner_Partners  |  07_Market_Research

4. MVP SCOPE — LOCKED

| Side | Feature | MVP Definition | Priority |
| --- | --- | --- | --- |
| User | Find | Search by location, stay type and basic filters; show matching properties. | P0 |
| User | View Property | Photos, name, location, price, availability, verification status and amenities. | P0 |
| User | Basic Property Information | Type, price, sharing/private option, amenities, rules, beds/rooms, location and verification info. | P0 |
| User | Contact / Booking Request | Name, phone, preferred date, simple request/message, contact/WhatsApp, confirmation. | P0 |
| Owner | Submit Property | Owner + property details, price, amenities, photos and availability. | P0 |
| Owner/Admin | Property Verification | Manual status: Submitted → Under Review → Verified / Changes Required. | P0 |
| Owner | Manage Basic Listing | Edit listing, price, availability, photos, enquiries and verification status. | P0 |

Explicitly out of MVP: online payments, complex booking engine, reviews/ratings, referral/loyalty, AI chatbot, advanced recommendations, automatic OTA synchronization, advanced owner analytics, website ads, unnecessary redesigns.

5. OWNER VALIDATION SCRIPT

Target first five: Vijay Cozy Corner Hostel, StayZone Hostels, Marshal Enterprise, Deccan PG & Hostel, Sai Fortune Hostel.

30-second explanation:

“I’m with Hopebed — we help PG and hostel owners in Panvel and Navi Mumbai get direct, verified enquiries without broker dependency. We’re onboarding our first 20 partner properties with a free 3-month pilot, no upfront cost and no brokerage. I’d like to understand how you currently handle vacancies and enquiries and see whether Hopebed could help.”

1. How many platforms are you currently listed on, and how much time per week do you spend keeping availability updated?

2. When a bed becomes vacant, what is your process for finding the next tenant, and how long does it usually take?

3. How many enquiries from your current platforms actually convert into tenants?

4. How do you manage tenant enquiries today — mostly WhatsApp, phone, or something else? Do you ever lose leads because of delayed replies?

5. If a free tool could help you get verified enquiries and manage your property listing, what would make you trust it enough to try?

Record after every conversation:

☐ Biggest booking problem

☐ Current booking / lead sources

☐ Broker dependency or commission issue

☐ WhatsApp / response-time issue

☐ Willingness to list on Hopebed: Yes / No / Maybe

☐ Biggest objection

☐ Next step / follow-up date

6. DECISION GATES & KPIs

| Metric | Target | Status | CEO Decision |
| --- | --- | --- | --- |
| Website QA | All critical checks pass | ☐ | Release for testing / fix blockers |
| GA4 | Realtime data confirmed | DONE | Keep tracking active |
| Owner conversations | 5 completed | ☐ | Proceed / adjust pitch |
| Owners willing to list | At least 1–2 | ☐ | Start pilot onboarding |
| MVP flow | User + owner flows work | ☐ | Move to pilot testing |
| Business foundation | Documents organized; open compliance items known | ☐ | Schedule CA/legal actions |

7. CEO RULES FOR THE NEXT 3 DAYS

1. Evidence over assumptions: every major product decision should connect to an owner/user problem.

2. Protect MVP focus: do not add features just because competitors have them.

3. Use real owner language: capture exact words, objections and workflows from interviews.

4. Keep the current Hopebed design unless QA reveals a real usability problem.

5. Do not add ads to the MVP.

6. Do not build payment complexity before demand and booking behavior are validated.

7. End every day with a written decision: what was learned, what changed, and what happens next.

CEO END-OF-3-DAY SCORECARD

| Website | Owners | Pilot | MVP | Business |
| --- | --- | --- | --- | --- |
| ☐ | ☐ | ☐ | ☐ | ☐ |

Founder principle: Build less. Learn faster. Earn trust first.