## MVP Scope
HOPEBED — MVP FINAL SCOPE
Priority | Side | Feature | MVP Definition | Status
P0 | User | Find | Search by location, stay type and basic budget/filter options; show matching properties. | Not Started
P0 | User | View Property | Show photos, name, location, price, availability, verification status and amenities. | Not Started
P0 | User | Basic Property Information | Show type, price, sharing/private option, amenities, rules, available beds/rooms, location, verification info and contact. | Not Started
P0 | User | Contact / Booking Request | Collect name, phone, preferred date and simple request/message; provide contact/WhatsApp; show confirmation. | Not Started
P0 | Owner | Submit Property | Owner can submit name, phone, property details, location, type, rooms/beds, price, amenities, photos and availability. | Not Started
P0 | Owner/Admin | Property Verification | Manual workflow: Submitted → Under Review → Verified / Changes Required. | Not Started
P0 | Owner | Manage Basic Listing | Owner can view/edit listing, update price and availability, manage photos, view enquiries and verification status. | Not Started

## Out of Scope
HOPEBED — NOT IN MVP
Feature | Decision | Reason
Online payments | Exclude | Validate demand and booking flow before adding payment complexity.
Complex booking engine | Exclude | Use a simple contact/booking request first.
Reviews & ratings | Exclude | Add after core marketplace behavior is validated.
Referral / loyalty programs | Exclude | Not required for first release.
AI chatbot | Exclude | Not essential to validate the marketplace.
Advanced recommendation engine | Exclude | Start with search and basic filters.
Automatic multi-OTA synchronization | Exclude | Too complex for first release.
Advanced owner analytics dashboard | Exclude | Basic listing and enquiries are sufficient.
Website advertisements | Exclude | Keep the MVP clean and focused.
Unnecessary extra pages / redesigns | Exclude | Preserve current Hopebed brand and homepage direction.

## Acceptance Checklist
HOPEBED — MVP ACCEPTANCE CHECKLIST
ID | Acceptance Test | Status | Notes
MVP-01 | User can find a property by location. | Not Started
MVP-02 | User can open a property and understand the basic offer quickly. | Not Started
MVP-03 | Verified status is clearly visible on verified listings. | Not Started
MVP-04 | User can submit a contact/booking request. | Not Started
MVP-05 | Owner can submit a property for review. | Not Started
MVP-06 | Property can move through manual verification status. | Not Started
MVP-07 | Owner can edit availability and price. | Not Started
MVP-08 | Owner can view incoming enquiries. | Not Started
MVP-09 | Mobile flow works without horizontal scrolling. | Not Started
MVP-10 | Desktop flow works without broken navigation. | Not Started
MVP-11 | GA4 remains active and no website ads are added. | Done | GA4 already verified; ads intentionally excluded

## Dashboard
HOPEBED — MVP DELIVERY DASHBOARD
Metric | Value
P0 features | 7
Done | 0
In Progress | 0
Fail | 0
Acceptance tests passed | 0